## BACKLOG
ID | Imp | Name | User Story | Notes | How to test | Estimate
101 | 1 | Administrator can login | As administrator, I want to be able to log in so that I can use features of administrator account. | Administrator have a defualt login details with username(admin) and password(password). Page premiumlibrary.html get updated via jQuiry. | Open home page of premium library web site. Click on login link. Log in page opens. Click on admin button. Fill in administrator credentials into poped out dialog box and click login button. Admin account should open. | 23
102 | 2 | Administrator can create librarian account. | As administrator, I want to be able to create librarian account so that I can add new librarian. | After login, administrator can create new librarian account. Dependency on 101. | On successful login click New Librarian button, fill in details of new librarian and click save. New librarian row should be cteated in librarian table in database. | 20
103 | 3 | Administrator can update librarian account. | As administrator, I want to be able to update librarian account so that I can update details of librarian. | After login, administrator can update selected librarian account. Dependency on 101, 102 | On successful login click on one of listed librarians to list details of that librarian. Then fill in new details of selected librarian and click save. Librarian row should be updated with new details in librarian table in database. | 20
104 | 4 | Administrator can view librarian accounts. | As administrator, I want to be able to view all details of all librarians contained in library database so that I can see all details of each librarian account. | After login, administrator can view all librarians accounts. Dependency on 101, 102 | On successful login click on one of listed librarians to list details of that librarian. | 20
105 | 5 | Administrator can delete librarian account. | As administrator, I want to be able to delete librarians from library database so that I can remove librarian from librarians table in database if labrarian not working anymore in library. | After login, administrator can delete selected librarian account. Dependency on 101, 102 | On successful login click on one of listed librarians to list details of that librarian. Then click delete button. Selected librarian row should be removed from librarian table in database. | 15
106 | 6 | Administrator can logout | As administrator, I want to be able to log out from administrator account so that I can close it. | After logout the administrator account page close, home page containing login link opens. Dependency on 101 | When logout button is clicked, the administrator page should close and home page containing login link should open. Administrator account page now can be accessed only after successful login. | 15
201 | 7 | Librarian can login | As a Librarian, I want to be able to login into my account so that i can I can view my details. | Librarian login from via login link. Page premiumlibrary.html get updated via jQuiry to allow for login functionality. Dependency on 101, 102 | Open home page of premium library web site. Click on login link. Log in page opens. Click on Librarian button. Fill in librarian credentials into poped out dialog box and click login button. Librarian account should open. | 23
202 | 8 | Librarian can create customer account | As librarian I want to be able to create customer account so that I can add new customer. | After login, Librarian can create new customer account. Dependency on 201 | On successful login click Click for Customers button, then click New Customer button, then fill in details of new customer and click save. New customer row should be cteated in customer table in database. | 20
203 | 9 | Librarian can update customer account | As librarian I want to be able to update customer account so that I can change details of customer. | After login, Librarian can update selected customer account. Dependency on 201, 202 | On successful login click on one of listed customers to list details of that customer. Then fill in new details of selected customer and click save. Customer row should be updated with new details in customer table in database. | 20
204 | 10 | Librarian can view all customer accounts | As a Librarian, I want to be able to be able to view customers account so that I can see all details of all customers. | After login, librarian can view all customer accounts. Dependency on 201 | On successful login click on one of listed customers to list details of that customer. | 20
205 | 11 | Librarian can delete customers account | As a Librarian, I want to be able to delete customers account so that their information can be cleared off the system. | After login, librarian can delete selected customer account. Dependency on 201, 202 | On successful login click on one of listed customers to list details of that customer Then click delete button. Selected customer row should be removed from customer table in database. | 15
206 | 12 | Librarian can add books | As Librarian I want to be able to create a new book so that I can add more books to the library. | After login, Librarian can create new book Dependency on 201 | On successful login click Click for Books button, then click New Book button, then fill in details of new book and click save. New book row should be cteated in book table in database. | 30
207 | 13 | Librarian can update books | As Librarian I want to be able to update book so that I can change details of any book in the library. | After login, Librarian can update selected book details Dependency on 201, 202 | On successful login click on one of listed books to list details of that book Then fill in new details of selected book and click save. Book row should be updated with new details in book table in database. | 30
208 | 14 | Librarian can view books | As Librarian I want to be able to view all books so that I can see details of each book in library. | After login, librarian can view all books Dependency on 201 | On successful login click on one of listed books to list details of that book. | 25
209 | 15 | Librarian can delete books | As Librarian, I want to be able to delete books from library database so that I can update books table in database if book is removed from library. | After login, librarian can delete selected book. Dependency on 201, 202 | On successful login click on one of listed books to list details of that book. Then click delete button. Selected book row should be removed from book table in database. | 15
210 | 16 | Librarian can logout | As a Librarian, I want to be able to log out of my account when I'm no longer using it so that not body can access it. | After logout the librarian account page close, home page containing login link opens. Dependency on 201 | When logout button is clicked, the librarian page should close and home page containing login link should open. Librarian account page now can be accessed only after successful login. | 15
301 | 17 | Customers can view all books | As a customers, I want to be able to be able to view all books so that I can see what to borrow. | All books contained in library database with all the details related to each book should be desplayed on same page. | From home page click on Books button. All books should be listed. | 20
302 | 18 | Customers can search books by name | As a customers, I want to be able to search books by name so that I can easily find the books I am looking for by filtering search by book name. | Book name should be filled in | From home page click on Books button. Fill in book name and click search button. | 20
303 | 19 | Customers can search books by category | As a customers, I want to be able to search books by category so that I can easily find the books I am looking for by filtering search by book category. | Book category should be filled in | From home page click on Books button. Fill in book category and click search button. | 20
304 | 20 | Customers can search books by author | As a customers, I want to be able to search books by author so that I can easily find the books I am looking for by filtering search by book author. | Book author should be filled in | From home page click on Books button. Fill in book author and click search button. | 20
305 | 21 | Customers can login | As a customers, I want to be able to login to my account so that I can view my account. | Customer login from via login link. Page premiumlibrary.html get updated via jQuiry to allow for login functionality. Dependency on 202 | Open home page of premium library web site. Click on login link. Log in page opens. Click on Customers button. Fill in customer credentials into poped out dialog box and click login button. Customer account should open. | 20
306 | 22 | Customers view borrowed books | As a customers, I want to be able to view my account details so that i can see what books i have borrowed. | After login, customer can view all his borrowed books Dependency on 305 | On successful login click on one of listed boks to list details of that book | 20
307 | 23 | Customers can logout | As a customers, I want to be able to log out of my account when i'm no longer using it so that not body can access it. | After logout the customer account page close, home page containing login link opens. Dependency on 305 | When logout button is clicked, the customer page should close and home page containing login link should open. Customer account page now can be accessed only after successful login. | 15
308 | 24 | Customers can view library contact details | As a customers, I want to be able to view library contact details so that I can contact library if i need to. | Contact details are available via Contact Us link from home page. | Click Contact Us link on home page to display library contact details. | 15
309 | 25 | Customers can see map and location of library | As a customers, I want to be able to see map and location of library so that I can easily find my way there. | Map available via Contact Us link from home page. | Click Contact Us link on home page to display a map | 15
310 | 26 | Customers can reserve a book | As a customers, I want to be able to reserve a book so that it will be on hold for me. | Functionality added via jQuiry, back end APIs to be implemented. | to be defined | 25
311 | 27 | Customers can rent a book | As a customers, I want to be able to rent a book so that I could take it from library. | Functionality added via jQuiry, back end APIs to be implemented. | to be defined | 25
312 | 28 | Customers can return a book | As a customers, I want to be able to return a book so that I can bring it back and make it again available to other costomers. | Functionality added via jQuiry, back end APIs to be implemented. | to be defined | 25

## CARD
Backlog Item #101
Importance
| As administrator, I want to be able to log in so that I can use features of administrator account. | 1
| Notes | Estimate
| Administrator have a defualt login details with username(admin) and password(password). Page premiumlibrary.html get updated via jQuiry. | 23
How to demo
Open home page of premium library web site. Click on login link. Log in page opens. Click on admin button. Fill in administrator credentials into poped out dialog box and click login button. Admin account should open.
Backlog Item #102
Importance
| As administrator, I want to be able to create librarian account so that I can add new librarian. | 2
| Notes | Estimate
| After login, administrator can create new librarian account. Dependency on 101. | 20
How to demo
On successful login click New Librarian button, fill in details of new librarian and click save. New librarian row should be cteated in librarian table in database.
Backlog Item #103
Importance
| As administrator, I want to be able to create librarian account so that I can update details of librarian. | 3
| Notes | Estimate
| After login, administrator can update selected librarian account. Dependency on 101, 102 | 20
How to demo
On successful login click on one of listed librarians to list details of that librarian. Then fill in new details of selected librarian and click save. Librarian row should be updated with new details in librarian table in database.
Backlog Item #104
Importance
| As administrator, I want to be able to view all details of all librarians contained in library database so that I can see all details of each librarian account. | 4
| Notes | Estimate
| After login, administrator can view all librarians accounts. Dependency on 101, 102 | 20
How to demo
On successful login click on one of listed librarians to list details of that librarian.
Backlog Item #105
Importance
| As administrator, I want to be able to delete librarians from library database so that I can remove librarian from librarians table in database if labrarian not working anymore in library. | 5
| Notes | Estimate
| After login, administrator can delete selected librarian account. Dependency on 101, 102 | 15
How to demo
On successful login click on one of listed librarians to list details of that librarian. Then click delete button. Selected librarian row should be removed from librarian table in database.
Backlog Item #106
Importance
| As administrator, I want to be able to log out from administrator account so that I can close it. | 6
| Notes | Estimate
| After logout the administrator account page close, home page containing login link opens. Dependency on 101 | 15
How to demo
When logout button is clicked, the administrator page should close and home page containing login link should open. Administrator account page now can be accessed only after successful login.
Backlog Item #201
Importance
| As a Librarian, I want to be able to login into my account so that i can I can view my details. | 7
| Notes | Estimate
| Librarian login from via login link. Page premiumlibrary.html get updated via jQuiry to allow for login functionality. Dependency on 101, 102 | 23
How to demo
Open home page of premium library web site. Click on login link. Log in page opens. Click on Librarian button. Fill in librarian credentials into poped out dialog box and click login button. Librarian account should open.
Backlog Item #202
Importance
| As librarian I want to be able to create customer account so that I can add new customer. | 8
| Notes | Estimate
| After login, Librarian can create new customer account. Dependency on 201 | 20
How to demo
On successful login click Click for Customers button, then click New Customer button, then fill in details of new customer and click save. New customer row should be cteated in customer table in database.
Backlog Item #203
Importance
| As librarian I want to be able to update customer account so that I can change details of customer. | 9
| Notes | Estimate
| After login, Librarian can update selected customer account. Dependency on 201, 202 | 20
How to demo
On successful login click on one of listed customers to list details of that customer. Then fill in new details of selected customer and click save. Customer row should be updated with new details in customer table in database.
Backlog Item #204
Importance
| As a Librarian, I want to be able to be able to view customers account so that I can see all details of all customers. | 10
| Notes | Estimate
| After login, librarian can view all customer accounts. Dependency on 201 | 20
How to demo
On successful login click on one of listed customers to list details of that customer.
Backlog Item #205
Importance
| As a Librarian, I want to be able to delete customers account so that their information can be cleared off the system. | 11
| Notes | Estimate
| After login, librarian can delete selected customer account. Dependency on 201, 202 | 15
How to demo
On successful login click on one of listed customers to list details of that customer Then click delete button. Selected customer row should be removed from customer table in database.
Backlog Item #206
Importance
| As Librarian I want to be able to create a new book so that I can add more books to the library. | 12
| Notes | Estimate
| After login, Librarian can create new book Dependency on 201 | 30
How to demo
On successful login click Click for Books button, then click New Book button, then fill in details of new book and click save. New book row should be cteated in book table in database.
Backlog Item #207
Importance
| As Librarian I want to be able to update book so that I can change details of any book in the library. | 13
| Notes | Estimate
| After login, Librarian can update selected book details Dependency on 201, 202 | 30
How to demo
On successful login click on one of listed books to list details of that book Then fill in new details of selected book and click save. Book row should be updated with new details in book table in database.
Backlog Item #208
Importance
| As Librarian I want to be able to view all books so that I can see details of each book in library. | 14
| Notes | Estimate
| use drop down list to select and customers should be able to see the book they borrowed | 25
How to demo
On successful login click on one of listed books to list details of that book.
Backlog Item #209
Importance
| As Librarian, I want to be able to delete books from library database so that I can update books table in database if book is removed from library. | 15
| Notes | Estimate
| After login, librarian can delete selected book. Dependency on 201, 202 | 15
How to demo
On successful login click on one of listed books to list details of that book. Then click delete button. Selected book row should be removed from book table in database.
Backlog Item #210
Importance
| As a Librarian, I want to be able to log out of my account when I'm no longer using it so that not body can access it. | 16
| Notes | Estimate
| After logout the librarian account page close, home page containing login link opens. Dependency on 201 | 15
How to demo
When logout button is clicked, the librarian page should close and home page containing login link should open. Librarian account page now can be accessed only after successful login.
Backlog Item #301
Importance
| As a customers, I want to be able to be able to view all books so that I can see what to borrow. | 17
| Notes | Estimate
| All books contained in library database with all the details related to each book should be desplayed on same page. | 20
How to demo
From home page click on Books button. All books should be listed.
Backlog Item #302
Importance
| As a customers, I want to be able to search books by name so that I can easily find the books I am looking for by filtering search by book name. | 18
| Notes | Estimate
| Book name should be filled in | 20
How to demo
From home page click on Books button. Fill in book name and click search button.
Backlog Item #303
Importance
| As a customers, I want to be able to search books by category so that I can easily find the books I am looking for by filtering search by book category. | 19
| Notes | Estimate
| Book category should be filled in | 20
How to demo
From home page click on Books button. Fill in book category and click search button.
Backlog Item #304
Importance
| As a customers, I want to be able to search books by author so that I can easily find the books I am looking for by filtering search by book author. | 20
| Notes | Estimate
| Book author should be filled in | 20
How to demo
From home page click on Books button. Fill in book author and click search button.
Backlog Item #305
Importance
| As a customers, I want to be able to login to my account so that I can view my account. | 21
| Notes | Estimate
| Customer login from via login link. Page premiumlibrary.html get updated via jQuiry to allow for login functionality. Dependency on 202 | 20
How to demo
Open home page of premium library web site. Click on login link. Log in page opens. Click on Customers button. Fill in customer credentials into poped out dialog box and click login button. Customer account should open.
Backlog Item #306
Importance
| As a customers, I want to be able to view my account details so that i can see what books i have borrowed. | 22
| Notes | Estimate
| After login, customer can view all his borrowed books Dependency on 305 | 20
How to demo
On successful login click on one of listed boks to list details of that book
Backlog Item #307
Importance
| As a customers, I want to be able to log out of my account when i'm no longer using it so that not body can access it. | 23
| Notes | Estimate
| After logout the customer account page close, home page containing login link opens. Dependency on 305 | 15
How to demo
When logout button is clicked, the customer page should close and home page containing login link should open. Customer account page now can be accessed only after successful login.
Backlog Item #308
Importance
| As a customers, I want to be able to view library contact details so that I can contact library if i need to. | 24
| Notes | Estimate
| Contact details are available via Contact Us link from home page. | 15
How to demo
LClick Contact Us link on home page to display library contact details.
Backlog Item #309
Importance
| As a customers, I want to be able to see map and location of library so that I can easily find my way there. | 25
| Notes | Estimate
| Map available via Contact Us link from home page. | 15
How to demo
Click Contact Us link on home page to display a map

## TEMPLATE
Backlog item #1001
Importance
| As a Manager, I want to be able to create management staff account. | 1
| Notes | Estimate
| Username is employee ID (PM001xxxx) this is for the first Management account with auto increment for the next Management account. Password should be at least 6 alpha numberic. | 40
How to demo
Management can create account by providing their details.