## BACKLOG
ID | Imp | Name | User Story | Notes | How to test | Estimate
401 | 1 | Api user Retrieve Admin login details | As an Api User, I want to be able to send Get query to library database so that I can extract admin login data from Admin table and return in Json format. | Send query via Postman using GET HTTP method | Send query via Postman using GET HTTP method, type in correct URI: http://localhost:8080/PremiumLibraryTeam/rest/admin data from admin table should be displayed back | 25
402 | 2 | Api user Retrieve All customers data | As an Api User, I want to be able to send Get query to library database so that I can extract all customers data from customers table and return in Json format. | Send query via Postman using GET HTTP method | Send query via Postman using GET HTTP method, type in correct URI: http://localhost:8080/PremiumLibraryTeam/rest/customers data from admin table should be displayed back. | 25
403 | 3 | Api user Retrieve customer data by Email | As an Api User, I want to be able to send Get query to library database so that I can find and extract customers data from customers table using customers email and return in Json format. | Send query via Postman using GET HTTP method and search path | Send query via Postman using GET HTTP method, type in correct URI: http://localhost:8080/PremiumLibraryTeam/rest/search/"name" data from admin table should be displayed back | 25
404 | 4 | Api user Create Customer | As an Api User, I want to be able to send Post query to library database so that I can create new Customer row in Customers table. | Send query via Postman using POST HTTP method | Type in correct URI: http://localhost:8080/PremiumLibraryTeam/rest/books Send query via Postman, type in body message in JSON format: { "id": 3, "bookAuthor": "Real Author", "bookName": "Real", "bookReserved": false, "bookCategory": "Real book category", "bookRented": true, "bookReservedUserId": 1, "bookDescription": "Real book description", "bookRentedUserId": 2, "bookRentedDate": "2016-12-21" } Set message header Content-Type as application/json New table row should be created. | 30
405 | 5 | Api user Update Customers | As an Api User, I want to be able to send PUT query to library database so that I can Update specific data in Customers table. | Send query via Postman using PUT HTTP method | Type in correct URI: http://localhost:8080/PremiumLibraryTeam/rest/books Send query via Postman, type in body message in JSON format: { "id": 3, "bookAuthor": "Real Author", "bookName": "Real", "bookReserved": false, "bookCategory": "Real book category", "bookRented": true, "bookReservedUserId": 1, "bookDescription": "Real book description", "bookRentedUserId": 2, "bookRentedDate": "2016-12-21" } Set message header Content-Type as application/json New table row should be created. | 25
406 | 6 | Api user Delete Customers | As an Api User, I want to be able to send Delete query to library database so that I can Delete specific row in Customers table. | Send query via Postman using DELETE HTTP method | Type in correct URI: http://localhost:8080/PremiumLibraryTeam/rest/books Send query via Postman, type in body message in JSON format: { "id": 3, "bookAuthor": "Real Author", "bookName": "Real", "bookReserved": false, "bookCategory": "Real book category", "bookRented": true, "bookReservedUserId": 1, "bookDescription": "Real book description", "bookRentedUserId": 2, "bookRentedDate": "2016-12-21" } Set message header Content-Type as application/json New table row should be created. | 20
407 | 7 | Api user Retrieve All Librarian data | As an Api User, I want to be able to send Get query to library database so that I can extract all Librarians data from Librarians table and return in Json format. | Send query via Postman using GET HTTP method | Same way as for admin | 25
408 | 8 | Api user Create Librarian | As an Api User, I want to be able to send Post query to library database so that I can create new Librarian row in Librarians table. | Send query via Postman using POST HTTP method | Type in correct URI: http://localhost:8080/PremiumLibraryTeam/rest/books Send query via Postman, type in body message in JSON format: { "id": 3, "bookAuthor": "Real Author", "bookName": "Real", "bookReserved": false, "bookCategory": "Real book category", "bookRented": true, "bookReservedUserId": 1, "bookDescription": "Real book description", "bookRentedUserId": 2, "bookRentedDate": "2016-12-21" } Set message header Content-Type as application/json New table row should be created. | 30
409 | 9 | Api user Update Librarian | As an Api User, I want to be able to send PUT query to library database so that I can Update specific data in Librarians table. | Send query via Postman using PUT HTTP method |  | 25
410 | 10 | Api user Delete Librarian | As an Api User, I want to be able to send Delete query to library database so that I can Delete specific row in Librarians table. | Send query via Postman using DELETE HTTP method | Same way as for book | 20
411 | 11 | Api user Retrieve All Book data | As an Api User, I want to be able to send Get query to library database so that I can extract all books data from books table and return in Json format. | Send query via Postman using GET HTTP method | Same way as for admin | 25
412 | 12 | Api user Retrieve Book data by ID | As an Api User, I want to be able to send Get query to library database so that I can find and extract books data from books table using Book ID and return in Json format. | Send query via Postman using GET HTTP method and id path | Send query via Postman using GET HTTP method, type in correct URI: http://localhost:8080/PremiumLibraryTeam/rest/book/"ID" data from admin table should be displayed back | 25
413 | 13 | Api user Retrieve Book data by Name | As an Api User, I want to be able to send Get query to library database so that I can find and extract books data from books table using Book Name and return in Json format. | Send query via Postman using GET HTTP method and search path | Send query via Postman using GET HTTP method, type in correct URI: http://localhost:8080/PremiumLibraryTeam/rest/book/search/"name" data from admin table should be displayed back | 25
414 | 14 | Api user Retrieve Book data by Author | As an Api User, I want to be able to send Get query to library database so that I can find and extract books data from books table using Book Author and return in Json format. | Send query via Postman using GET HTTP method and search path | Send query via Postman using GET HTTP method, type in correct URI: http://localhost:8080/PremiumLibraryTeam/rest/book/search/"name" data from admin table should be displayed back | 25
415 | 15 | Api user Create book | As an Api User, I want to be able to send Post query to library database so that I can create create new book row in books table. | Send query via Postman using POST HTTP method | Type in correct URI: http://localhost:8080/PremiumLibraryTeam/rest/books Send query via Postman, type in body message in JSON format: { "id": 3, "bookAuthor": "Real Author", "bookName": "Real", "bookReserved": false, "bookCategory": "Real book category", "bookRented": true, "bookReservedUserId": 1, "bookDescription": "Real book description", "bookRentedUserId": 2, "bookRentedDate": "2016-12-21" } Set message header Content-Type as application/json New table row should be created. | 30
416 | 16 | Api user Update Book | As an Api User, I want to be able to send PUT query to library database so that I can Update specific data in books table. | Send query via Postman using PUT HTTP method | Send query via Postman, type in body message in JSON format. Set message header Content-Type as application/json. Type in correct URI: http://localhost:8080/PremiumLibraryTeam/rest/books/1 Books table row 1 should be updated. | 25
417 | 17 | Api user Delete Book | As an Api User, I want to be able to send Delete query to library database so that I can Delete specific row in books table. | Send query via Postman using DELETE HTTP method | Send query via Postman, type in body message in JSON format. Set message header Content-Type as application/json. Type in correct URI: http://localhost:8080/PremiumLibraryTeam/rest/books/1 Books table row 1 should be deleted. | 20
101 | 18 | Administrator can login | As administrator, I want to be able to log in so that i can use features of administrator account. | Administrator have a defualt login details with username(admin) and password(password). Link to login page available in home page. Dependency on 401. | Open home page of premium library web site. Click on login link. Log in page opens. Fill in administrator credentials into login form and click submit button. If all details entered are correct, the administrator account page should open. | 23
102 | 19 | Administrator can view account | As administrator, I want to be able to view administrator account so that I can see all details and options of account. | After login, administrator can access all features of administrator account to be able to manage web site. Dependency on 101. | On successful login administrator account page should open and all administrative features should become available. | 20
107 | 20 | Administrator can create librarian account. | As administrator, I want to be able to create librarian account so that I can add new librarian. | Createte librarian form should be filled in with all details of new librarian. Dependency on 101,102,408 | On successful login administrator account page should open and "add librarian" link should become available. After entering all new librarian details into add librarian form and clicking submit button, a prompt should appear, confirming that new librarian was successfully added into database. | 20
108 | 21 | Administrator can view librarian accounts. | As administrator, I want to be able to view all details of all librarians contained in library database so that I can see all details of each librarian account. | All librarians contained in library database with all the details related to each librarian should be desplayed in one table. Dependency on 107, 407 | On successful login administrator account page should open and "librarians" link should become available. Display scrollable librarians table containing details of all librarians in database. | 10
201 | 22 | Librarian can login | As a Librarian, I want to be able to login into my account so that i can I can view my details. | Message should promot up if librarian puts in invalid password or username while trying to log into there account. Dependency on 107. | Enter browser, Navigate "log in" enter your details and click log in. Librarian acount should display. | 23
202 | 23 | Librarian can view account | As a Librarian, I want to be able to view my account so that i can create customers account. | Librarians should be able to see all their detials including their password. Dependency on 201. | Log-in, once logged in all librarian account details will be displayed. | 20
204 | 24 | Librarian can create customer account | As a Librarian, I want to be able to be able to create customers account so that I can edit their details. | Create customer form should be filled in with all details of new customer. Dependency on 202, 404 | Similar to create librarian - 107 | 20
205 | 25 | Librarian can view all customer accounts | As a Librarian, I want to be able to be able to view customers account so that I can see whether their details is correct. | All customers contained in library database with all the details related to each customer should be desplayed in one table. Dependency on 202, 402 | Similar to view all librarians accounts - 108 | 10
302 | 26 | Customers can login | As a customers, I want to be able to login to my account so that i can view my account. | Similar librarian can log in - 201 Dependency on 204 | Similar librarian can log in - 201 | 23
303 | 27 | Customers view his account | As a customers, I want to be able to view my account so that i can see what books i have borrowed. | Similar to Librarian can view account - 202 Dependency on 302 | Similar to Librarian can view account - 202 | 20
214 | 28 | Librarian can add books | As Librarian I want to be able to add books into library database so that I can add more books to the library. | All details related to book should be entered before submitting request to database - book name, book author and book category. Dependency on 201, 415 | On successful login Librarian account page should open and "add book" link should become available. After entering all book details into add book form and clicking submit button, a prompt should appear, confirming that book was successfully added. | 30
215 | 29 | Librarian can view books | As Librarian I want to be able to view all books details contained in library database so that I can see details of each book in library. | All books contained in library database with all the details related to each book should be desplayed in one table. Dependency on 201, 411 | On successful login Librarian account page should open and "books" link should become available. On click, "books" display scrollable books table containing details of all books in database, including details on books availability colmn. | 25
305 | 30 | Customers can view all books | As a customers, I want to be able to be able to view all books so that I can see what to borrow. | All books contained in library database with all the details related to each book should be desplayed in one table. Dependency on 302, 411 | Once login is successful, an option to view all all books should be displayed, click on it to display all books including details on books availability colmn. | 20
208 | 31 | Librarian can lend out books | As a Librarian, I want to be able to lend out book so that we can keep account of the books available. | Lended books are displayed in the customers coounts details. Dependency on 201 | Once login is successful, an option to lend out a books should be available. On click, fill all related book and customer details into lend a book form, click submit. I will update customer database table and books table. | 25
209 | 32 | Librarian can accept returning books | As a Librarian, I want to be able to accept returning books so that we can keep account of the books available. | Lended books are displayed in the customers coounts details. Dependency on 201 | Once login is successful, an option to accept a books should be available. On click, fill all related book and customer details into accept a book form, click submit. I will update customer database table and books table. | 20
216 | 33 | Librarian can delete books | As Librarian, I want to be able to delete books from library database so that I can update books table in database if book is removed from library. | Each book row in books table in book page contains delete link in one of row cells. Dependency on 101,102, 104, 105. | When "books" page is open and books table available, it should be posssible to scroll to table row which contains details of required book. Then after clicking delete link in the book row, database and books page books table get updated, deleted book details removed. | 5
304 | 34 | Customers can logout | As a customers, I want to be able to log out of my account when i'm no longer using it so that not body can access it. | Similar button as login Dependency on 302 | Log-in Navigate "Log-out” click logout button home page will be displayed so that no other person can have access to it. | 5
203 | 35 | Librarian can logout | As a Librarian, I want to be able to log out of my account when i'm no longer using it so that not body can access it. | Similar button as login Dependency on 201 | Log-in Navigate "Log-out” click logout button home page will be displayed so that no other person can have access to it. | 5
103 | 36 | Administrator can logout | As administrator, I want to be able to log out from administrator account so that I can close it. | After logout the administrator account page close, home page containing login link opens. Dependency on 101 | When logout button is clicked, the administrator page should close and home page containing login link should open. Administrator account page now can be accessed only after successful login. | 5
307 | 37 | Customers can search available books by name | As a customers, I want to be able to search books by name so that I can easily find the books im looking by filtering it. | SQL "sellect all books where name =*****;" | Once login is successful, an option to view all all books should be displayed, click on search book by name button, all book with the name typed will be displayed | 20
308 | 38 | Customers can search available books by Author | As a customers, I want to be able to search books by author so that I can easily find the books im looking by filtering it. | SQL "sellect all books where author =*****;" | Once login is successful, an option to view all all books should be displayed, click on search book by author button, all book with the author typed will be displayed | 20
309 | 39 | Customers can search available books by category | As a customers, I want to be able to search books by catergory so that I can easily find the books im looking by filtering it. | SQL "sellect all books where category =*****;" | Once login is successful, an option to view all all books should be displayed, click on search book by category button, all book with the category typed will be displayed | 20
211 | 40 | Librarian can search books by name | As a Librarian, I want to be able to search books by name so that I can easily for find the books im looking by filtering it. | Similar design as login button | Enter brower, "click login" option will be displayed, select Librarian, enter details, once login is successful, an option to view all all books should be displayed, click on search book by name button, all book with the name typed will be displayed | 20
212 | 41 | Librarian can search book by author | As a Librarian, I want to be able to search books by author so that I can easily for find the books im looking by filtering it. | Similar design as login button | Enter brower, "click login" option will be displayed, select Librarian, enter details, once login is successful, an option to view all all books should be displayed, click on search book by author button, all book with the author typed will be displayed | 20
213 | 42 | Librarian can search book by category | As a Librarian, I want to be able to search books by catergory so that I can easily for find the books im looking by filtering it. | Similar design as login button | Enter brower, "click login" option will be displayed, select Librarian, enter details, once login is successful, an option to view all all books should be displayed, click on search book by catergory button, all book with the catergory typed will be displayed | 20
310 | 43 | Customers can reserve a book | As a customers, I want to be able to reserve a book so that it will be on hold for me. | Just a button | Once login is successful, an option to view all all books should be displayed, click on it to display all books, select a book , click on borro to reserve it. | 20
210 | 44 | Librarian can view reserved customers books | As a Librarian, I want to be able to view reserved customers books so that we can keep it on hold for them. | Similar button as login | Enter brower, "click login" option will be displayed, select Librarian, enter details, once login is successful, an option to view all all books should be displayed, click on the books reserved button, all the book should be displayed. | 20
311 | 45 | Customers can view library contact details | As a customers, I want to be able to view library contact details so that I can call them if i need to. | HTML static contact page with library details | From the home page, navigate to"contact.html". The library contact details should be displayed. | 10
312 | 46 | Customers can see map and location of library | As a customers, I want to be able to see map and location of library so that I can easily find my way there. | HTML static contact page with embeded google map. | From the home page, navigate to"contact.html". An embeded map should display the library location. | 15
206 | 47 | Librarian can delete customers account | As a Librarian, I want to be able to delete customers account so that their information can be cleared off the system. | Similar button as login | Enter brower, "click login" option will be displayed, select Librarian, enter details, once login is successful, an option to view all customers should be displayed, click on delete customer which ever needs to be deleted | 5
109 | 48 | Administrator can delete librarian account. | As administrator, I want to be able to delete librarians from library database so that I can update librarians table in database if labrarian not working anymore in library. | Each librarian row in librarians table in librarians page contains delete link in one of row cells. Dependency on 101,102, 107,108. | When "librarians" page is open and librarians table available, it should be possible to scroll to table row which contains details of required librarian. Then after clicking delete link in the corresponding librarians table row, database and librarians table on librarians page get updated, deleted librarian details removed. | 5

## CARD
Backlog Item #101
Importance
| As administrator, I want to be able to log in so that I can use features of administrator account. | 18
| Notes | Estimate
| Administrator havs a defualt login details with username(xxx) and password(yyy). | 23
How to demo
Click on log in button "log in dialog box should display" enter administrator username and password.
Backlog Item #102
Importance
| As administrator, I want to be able to view administrator account so that I can see all details and options of account. | 19
| Notes | Estimate
| After login, administrator can access all features of administrator account to be able to manage web site. Dependency on 101. | 20
How to demo
Click on log in button "log in dialog box should display" enter administrator username and password.
Backlog Item #103
Importance
| As administrator, I want to be able to log out from administrator account so that I can close it. | 36
| Notes | Estimate
| After logout the administrator account page close, home page containing login link opens. Dependency on 101, 102. | 5
How to demo
While in administrator acccount page, click logout link.
Backlog Item #107
Importance
| As administrator, I want to be able to create librarian account so that I can add new librarian. | 20
| Notes | Estimate
| On librerians page createte librarian form should be fille in with all details of new librarian. Dependency on 101,102 | 20
How to demo
While in "add librerian" page, enter librerian details into add librerian form and click submit.
Backlog Item #108
Importance
| As administrator, I want to be able to view all details of all librarians contained in library database so that I can see all details of each librarian account. | 21
| Notes | Estimate
| All librarians contained in library database with all the details related to each librarian should be desplayed in one table. Dependency on 101,102, 107. | 10
How to demo
Open librarians page, librarians table should be displayed.
Backlog Item #109
Importance
| As administrator, I want to be able to delete librarians from library database so that I can update librarians table in database if labrarian not working anymore in library. | 48
| Notes | Estimate
| Each librarian row in librarians table in librarians page contains delete link in one of row cells. | 5
How to demo
Open librarians page, librarians table should be displayed. Scroll to table row which contains details of required librarian. Then after clicking delete link in the librarians row, database and librarians page librarians table get updated, deleted librarian details removed.
Backlog Item #201
Importance
| As a Librarian, I want to be able to login into my account so that i can I can view my details. | 22
| Notes | Estimate
| message should promot up if customer puts in invalid password or username while trying to log into there account | 23
How to demo
Enter browser, Navigate "log in" enter your details and click log in. Librarian acount should display.
Backlog Item #202
Importance
| As a Librarian, I want to be able to view my account so that i can create customers account. | 23
| Notes | Estimate
| Librarians should be able to see all there detials including their password | 20
How to demo
Log-in, once logged in Librarian detail page will be displayed straight.
Backlog Item #203
Importance
| As a Librarian, I want to be able to log out of my account when i'm no longer using it so that not body can access it. | 35
| Notes | Estimate
| Similar button as login | 5
How to demo
Log-in Navigate "Log-out” click logout button home page will be displayed so that no other person can have access to it.
Backlog Item #204
Importance
| As a Librarian, I want to be able to be able to create customers account so that I can edit their details. | 24
| Notes | Estimate
| similar design as the index page | 20
How to demo
Enter brower, "click login" an option will display on menu, click customer and enter customer's details.
Backlog Item #205
Importance
| As a Librarian, I want to be able to be able to view customers account so that I can see whether their details is correct. | 25
| Notes | Estimate
| Similar to librarian account | 10
How to demo
Enter browser, click Log-in, enter customer's details, customers account should be displayed.
Backlog Item #206
Importance
| As a Librarian, I want to be able to delete customers account so that their information can be cleared off the system. | 47
| Notes | Estimate
| Similar button as login | 5
How to demo
Enter brower, "click login" option will be displayed, select Librarian, enter details, once login is successful, an option to view all customers should be displayed, click on delete customer which ever needs to be deleted
Backlog Item #207
Importance
| As a Librarian, I want to be able to view available books so that I can see all books available. | 28
| Notes | Estimate
| Similar button as login | 20
How to demo
Enter brower, "click login" option will be displayed, select Librarian, enter details, once login is successful, an option to view all all books should be displayed, click on the button and all the books will be displayed.
Backlog Item #208
Importance
| As a Librarian, I want to be able to lend out book so that we can keep account of the books available. | 31
| Notes | Estimate
| use drop down list to select and customers should be able to see the book they borrowed | 25
How to demo
Enter brower, "click login" option will be displayed, select Librarian, enter details, once login is successful, an option to view all all books should be displayed, select the book that's needed and click lend.
Backlog Item #209
Importance
| As a Librarian, I want to be able to accept returning books so that we can keep account of the books available. | 32
| Notes | Estimate
| use drop down list to select and customers should be able to see the book they borrowed | 20
How to demo
Enter brower, "click login" option will be displayed, select Librarian, enter details, once login is successful, an option to view all all books should be displayed, select the book that's needed and click return.
Backlog Item #210
Importance
| As a Librarian, I want to be able to view reserved customers books so that we can keep it on hold for them. | 44
| Notes | Estimate
| Similar button as login | 20
How to demo
Enter brower, "click login" option will be displayed, select Librarian, enter details, once login is successful, an option to view all all books should be displayed, click on the books reserved button, all the book should be displayed.
Backlog Item #211
Importance
| As a Librarian, I want to be able to search books by name so that I can easily for find the books im looking by filtering it. | 40
| Notes | Estimate
| Similar design as login button | 20
How to demo
Enter brower, "click login" option will be displayed, select Librarian, enter details, once login is successful, an option to view all all books should be displayed, click on search book by name button, all book with the name typed will be displayed
Backlog Item #212
Importance
| As a Librarian, I want to be able to search books by author so that I can easily for find the books im looking by filtering it. | 41
| Notes | Estimate
| Similar design as login button | 20
How to demo
Enter brower, "click login" option will be displayed, select Librarian, enter details, once login is successful, an option to view all all books should be displayed, click on search book by author button, all book with the author typed will be displayed
Backlog Item #213
Importance
| As a Librarian, I want to be able to search books by catergory so that I can easily for find the books im looking by filtering it. | 42
| Notes | Estimate
| Similar design as login button | 20
How to demo
Enter brower, "click login" option will be displayed, select Librarian, enter details, once login is successful, an option to view all all books should be displayed, click on search book by catergory button, all book with the catergory typed will be displayed
Backlog Item #214
Importance
| As librarian I want to be able to add books into library database so that I can add more books to the library | 28
| Notes | Estimate
| All details related to book should be entered before submitting request to database - book name, book author and book category. | 30
How to demo
While in "add book" page, enter book details into add book form and click submit.
Backlog Item #215
Importance
| As librarian I want to be able to view all books details contained in library database so that I can see details of each book in library. | 29
| Notes | Estimate
| All books contained in library database with all the details related to each book should be desplayed in one table. | 25
How to demo
Open "books" page, books table should be displayed.
Backlog Item #216
Importance
| As librarian I want to be able to delete books from library database so that I can update books table in database if book is removed from library. | 33
| Notes | Estimate
| Each book row in books table in book page contains delete link in one of row cells. Dependency on 101,102, 104, 105. | 5
How to demo
Open books page, books table should be displayed. Scroll to table row which contains details of required book. Then after clicking delete link in the book row, database and books page books table get updated, deleted book details removed.
Backlog Item #302
Importance
| As a customers, I want to be able to login to my account so that i can view my account. | 26
| Notes | Estimate
| Similar button as login for everyone | 23
How to demo
Enter browser, Navigate "log in" enter your details and click log in. Customers acount should display.
Backlog Item #303
Importance
| As a customers, I want to be able to view my account so that i can see what books i have borrowed. | 27
| Notes | Estimate
| Customers page after login in | 20
How to demo
Log-in, once logged in customers detail page will be displayed straight.
Backlog Item #304
Importance
| As a customers, I want to be able to log out of my account when i'm no longer using it so that not body can access it. | 34
| Notes | Estimate
| Just a button | 5
How to demo
Log-in Navigate "Log-out” click logout button home page will be displayed so that no other person can have access to it.
Backlog Item #305
Importance
| As a customers, I want to be able to be able to view all books so that I can see what to borrow. | 30
| Notes | Estimate
| Customers page after login in | 20
How to demo
Once login is successful, an option to view all all books should be displayed, click on it to display all books
Backlog Item #306
Importance
| As a customers, I want to be able to borrow books so that i can see the books i borrowed in my account. | 30
| Notes | Estimate
| Borrowed books is displayed in the customers page | 15
How to demo
Once login is successful, an option to view all all books should be displayed, click on it to display all books, select a book to see if it is avalable to borrow. Once borrowed, it will display in the customers account.
Backlog Item #307
Importance
| As a customers, I want to be able to search books by name so that I can easily find the books im looking by filtering it. | 37
| Notes | Estimate
| SQL "sellect all books where name =*****;" | 20
How to demo
Once login is successful, an option to view all all books should be displayed, click on search book by name button, all book with the name typed will be displayed
Backlog Item #308
Importance
| As a customers, I want to be able to search books by author so that I can easily find the books im looking by filtering it. | 38
| Notes | Estimate
| SQL "sellect all books where author =*****;" | 20
How to demo
Once login is successful, an option to view all all books should be displayed, click on search book by author button, all book with the author typed will be displayed
Backlog Item #309
Importance
| As a customers, I want to be able to search books by catergory so that I can easily find the books im looking by filtering it. | 39
| Notes | Estimate
| SQL "sellect all books where category =*****;" | 20
How to demo
Once login is successful, an option to view all all books should be displayed, click on search book by category button, all book with the category typed will be displayed
Backlog Item #310
Importance
| As a customers, I want to be able to reserve a book so that it will be on hold for me. | 43
| Notes | Estimate
| Just a button | 20
How to demo
Once login is successful, an option to view all all books should be displayed, click on it to display all books, select a book , click on borro to reserve it.
Backlog Item #311
Importance
| As a customers, I want to be able to view library contact details so that I can call them if i need to. | 45
| Notes | Estimate
| HTML static contact page with library details | 10
How to demo
From the home page, navigate to"contact.html". The library contact details should be displayed.
Backlog Item #312
Importance
| As a customers, I want to be able to see map and location of library so that I can easily find my way there. | 46
| Notes | Estimate
| HTML static contact page with embeded google map. | 15
How to demo
From the home page, navigate to"contact.html". An embeded map should display the library location.
Backlog Item #401
Importance
| As an Api User, I want to be able to send Post query to library database so that I can create create new book row in books table. | 1
| Notes | Estimate
| Send query via Postman using POST HTTP method | 30
How to demo
Type in correct URI: http://localhost:8080/PremiumLibraryTeam/rest/books Send query via Postman, type in body message in JSON format: { "id": 3, "bookAuthor": "Real Author", "bookName": "Real", "bookReserved": false, "bookCategory": "Real book category", "bookRented": true, "bookReservedUserId": 1, "bookDescription": "Real book description", "bookRentedUserId": 2, "bookRentedDate": "2016-12-21" } Set message header Content-Type as application/json New table row should be created.
Backlog Item #402
Importance
| As an Api User, I want to be able to send Post query to library database so that I can create new Librarian row in Librarians table. | 2
| Notes | Estimate
| Send query via Postman using POST HTTP method | 30
How to demo
Same way as for book
Backlog Item #403
Importance
| As an Api User, I want to be able to send Post query to library database so that I can create new Customer row in Customers table. | 3
| Notes | Estimate
| Send query via Postman using POST HTTP method | 30
How to demo
Same way as for book
Backlog Item #404
Importance
| As an Api User, I want to be able to send Get query to library database so that I can extract admin login data from Admin table and return in Json format. | 4
| Notes | Estimate
| Send query via Postman using GET HTTP method | 25
How to demo
Send query via Postman using GET HTTP method, type in correct URI: http://localhost:8080/PremiumLibraryTeam/rest/admin data from admin table should be displayed back
Backlog Item #405
Importance
| As an Api User, I want to be able to send Get query to library database so that I can extract all books data from books table and return in Json format. | 5
| Notes | Estimate
| Send query via Postman using GET HTTP method | 25
How to demo
Same way as for admin
Backlog Item #406
Importance
| As an Api User, I want to be able to send Get query to library database so that I can extract all Librarians data from Librarians table and return in Json format. | 6
| Notes | Estimate
| Send query via Postman using GET HTTP method | 25
How to demo
Same way as for admin
Backlog Item #407
Importance
| As an Api User, I want to be able to send Get query to library database so that I can extract all customers data from customers table and return in Json format. | 7
| Notes | Estimate
| Send query via Postman using GET HTTP method | 25
How to demo
Same way as for admin
Backlog Item #408
Importance
| As an Api User, I want to be able to send PUT query to library database so that I can Update specific data in books table. | 8
| Notes | Estimate
| Send query via Postman using PUT HTTP method | 25
How to demo
Send query via Postman, type in body message in JSON format. Set message header Content-Type as application/json. Type in correct URI: http://localhost:8080/PremiumLibraryTeam/rest/books/1 Books table row 1 should be updated.
Backlog Item #409
Importance
| As an Api User, I want to be able to send PUT query to library database so that I can Update specific data in Librarians tab | 9
| Notes | Estimate
| Send query via Postman using PUT HTTP method | 25
How to demo
Same way as for book
Backlog Item #410
Importance
| As an Api User, I want to be able to send PUT query to library database so that I can Update specific data in Customers table. | 10
| Notes | Estimate
| Send query via Postman using PUT HTTP method | 25
How to demo
Same way as for book
Backlog Item #411
Importance
| As an Api User, I want to be able to send Delete query to library database so that I can Delete specific row in books table. | 11
| Notes | Estimate
| Send query via Postman using DELETE HTTP method | 20
How to demo
Send query via Postman, type in body message in JSON format. Set message header Content-Type as application/json. Type in correct URI: http://localhost:8080/PremiumLibraryTeam/rest/books/1 Books table row 1 should be deleted.
Backlog Item #412
Importance
| As an Api User, I want to be able to send Delete query to library database so that I can Delete specific row in Librarians table. | 12
| Notes | Estimate
| Send query via Postman using DELETE HTTP method | 20
How to demo
Same way as for book
Backlog Item #413
Importance
| As an Api User, I want to be able to send Delete query to library database so that I can Delete specific row in Customers table. | 13
| Notes | Estimate
| Send query via Postman using DELETE HTTP method | 20
How to demo
Same way as for book

## TEMPLATE
Backlog item #1001
Importance
| As a Manager, I want to be able to create management staff account. | 1
| Notes | Estimate
| Username is employee ID (PM001xxxx) this is for the first Management account with auto increment for the next Management account. Password should be at least 6 alpha numberic. | 40
How to demo
Management can create account by providing their details.